## Revision History
Document Revision Control Table
Version No. | Date Revised | Change Description | A/M/D (Add/Modify/Deleted) | Prepared By | Approved By
DEF01 | 2024-09-05 | General | Add | Bathul | Prof. Shilpi Dixit
DEF02 | 2024-09-05 | Labels | Modify | Bathul | Prof. Shilpi Dixit
DEF03 | 2024-09-05 | Inbox | Add | Bathul | Prof. Shilpi Dixit
DEF04 | 2024-09-05 | Accounts and Imports | Modify | Bathul | Prof. Shilpi Dixit
DEF05 | 2024-09-05 | Filters and Blocked Address | Add | Bathul | Prof. Shilpi Dixit
DEF06 | 2024-09-05 | Forwarding and POP/IMAP | Modify | Bathul | Prof. Shilpi Dixit

## Document Details
Project Name: Gmail Settings Functionality |  | Cleint ID Google
Module/Component Name: Settings |  | Sub-Module/Feature Name: General, Labels, Inbox, Accounts and Import, Filters and Blocked Addresses, Forwarding and POP/IMAP .
Test Case Name: Test of Gmail Settings Functionalities
Defect Log:
REFERENCE DOCUMENTS
Source Documents | Path |  | Version
Business Requirement Document | Test Case and Execution
Test Plan | Test Case and Execution
Defect Log | Test Case and Execution

## Defect Log
Test Case
|  | Prerequisites: |  | <Conditions that should be true to execute the test case>
|  | Assumptions: |  | <Scenarios that are assumed to be true for the test case> | [5 empty] | Verify on entering valid userid and password that the user/guest can login
Defect ID# | Defect Reporter | Defect Summary | Steps to Reproduce | Type of Defect | Expected Result | Actual Result | Environment | Software build version | Priority | Severity | Status | Date Open | Date Resolved
DEF01 | Bathul | 'In cycle 2 of the test case, The General gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the General settings link tab fails to respond with error message showing something went wrong | 1. launch a Chrome browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the General Tab | Web Based | Successfully land on the General Settings Tab. | Failed - The General settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.92 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05
DEF02 | Bathul | 'In cycle 1 of the test case, The Label gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the Label settings link tab fails to respond with error message showing something went wrong | 1. launch a Chrome browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the Labels Tab | Browser Versions | Successfully land on the Label Settings Tab. | Failed - The Label settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.93 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05
DEF03 | Bathul | 'In cycle 2 of the test case, The Inbox gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the Inbox settings link tab fails to respond with error message showing something went wrong | 1. launch a Chrome browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the Inbox Tab | Error Handling | Successfully land on the Inbox Settings Tab. | Failed - The Inbox settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.94 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05
DEF04 | Bathul | 'In cycle 1 of the test case, The Accounts and Imports gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the Accounts and Imports settings link tab fails to respond with error message showing something went wrong | 1. launch a Chrome browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the Accounts and Imports Tab | Functionality | Successfully land on the Accounts and Imports Settings Tab. | Failed - The Accounts and Imports settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.95 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05
DEF05 | Bathul | 'In cycle 2 of the test case, The Filters and Blocked Address gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the Filters and Blocked Address settings link tab fails to respond with error message showing something went wrong | 1. launch a browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the Filters and Blocked Tab | Web Based | Successfully land on the Filters and Blocked Address Settings Tab. | Failed - The Filters and Blocked Address settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.96 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05
DEF06 | Bathul | In cycle 1 of the test case, The Forwarding and POP/IMAP gmail settings link functionality needs to be validated. The prerequisites is that a chrome browser is installed and accessible to the internet. After launching the browser and accessing the given URL link the Forwarding and POP/IMAP settings link tab fails to respond with error message showing something went wrong | 1. launch a Chrome browser and access the given URL link 2. Click on the settings Icon and select See all settings 3. Click On the Forwarding and POP/IMAP Tab | Browser Versions | Successfully land on the Forwarding and POP/IMAP Settings Tab. | Failed - The Forwarding and POP/IMAP settings link is not responding | Windows Desktop OS 11/Chrome browser version - 130.0.6723.97 | Product build version - Current Version | High | Low | Open | 2024-09-05 | 2024-09-05